## Data and PM Scorecard
Global Interest Rate |  | 8%
Project ID | PM Name | Slacker Fee (Penalty for Negative Cash) | Hand-Shake Risk (Avg CO Lag Days) | Pay-Window Mismatch (Owner vs Sub Terms) | Labor Efficiency (Speed vs Budget) | Do-Over Rate (Owner-Rejected Invoices) |  | Metric | Red Flag (Light Red) | Green Flag (Light Green) | Range | Description | Calculation
P-101 Green Valley Site | Billy | -4000 | 9 | 30 | 0.83333 | 2.5% |  | Slacker Fee | Value is less than -$1,000.00 | Value is greater than or equal to $0.00 | Sheet3!C4:C8 | A penalty charge to the PM’s budget for every day their project stays in the "red." Penalizes PMs for being "the bank | (Total Days in Red) x (Daily Penalty Rate) x (Project Budget) OR (Negative Project Cash Position) $\times$ (Monthly Internal Interest Rate (arbitrary and manually set)).
P-102 Metro High Rise | Bonnie | -800 | 16 | 0 | 1.1111 | 0% |  | Hand-Shake Risk | Value is greater than 10 days | Value is less than or equal to 0 days | Sheet3!D4:D8 | How many days the PM let the crew work on a change before getting a signature. | Average of (Date Change Order Work Started) - (Date Change Order Signed by Owner)
P-103 NJ Steel Phase 3 | Bobby | -9600 | -4 | 45 | 1.1429 | 5.495% |  | Pay-Window Mismatch | Value is greater than 30 days | Value is less than or equal to 0 days | Sheet3!E4:E8 | When a PM pays a Sub in 30 days but the Owner doesn't pay us for 60. Flags cash-draining contracts. | Average of [(Owner Payment Term Days) - (Subcontractor Payment Term Days)] across all subs. Count of Subcontractors on "Net 30" terms vs. Owners on "Net 60" terms.
P-104 Board County Schools | Betty | 0 | 0 | -15 | 0.90909 | 3.03% |  | Labor Efficiency | Value is less than 0.90 | Value is greater than or equal to 1.10 | Sheet3!F4:F8 | Are we installing steel/dirt/pipe faster or slower than we estimated? | (Budgeted Hours for Task) / (Actual Hours Worked on Task). A value > 1 is inefficient.
P-105 Stadium Refurb | Becker | -6000 | 15 | 30 | 0.91667 | 4.054% |  | Do-Over Rate | Value is greater than 0.10 (10%) | Value is less than 10% | Sheet3!G4:G8 | How often an owner rejects our invoice because the PM made a mistake on the paperwork. | Total Count of Owner-Rejected Invoices due to PM Error over Total Number of Invoices Submitted.
Negative Project Cash Position | Change Order Start Date | Change Order Signed Date | Owner Payment Term (Days) | Subcontractor Payment Term (Days) | Actual Hours Worked on Task | Budgeted Hours for Task | Total Invoices Submitted | Owner-Rejected Invoices (due to PM Error) | Subcontractor Change Order Amounts | Internal Change Order Costs |  | What: Cash Flow Projection KPIs as crowdsourced from the CFMA forum & ad hoc workshops
-50000 | 2026-02-01 | 2026-02-10 | 60 | 30 | 180 | 150 | 80 | 2 | 15000 | 5000 |  | How to Use: take inspiration from the sample data, formulas, and conditional formatting in order to bring these metrics into your practice
-10000 | 2026-01-20 | 2026-02-05 | 30 | 30 | 90 | 100 | 45 | 0 | 8000 | 2500 |  | Who: Simple Analytics Framework workshop led by Datateer (Construction Data Analytics)
-120000 | 2026-03-05 | 2026-03-01 | 90 | 45 | 350 | 400 | 91 | 5 | 45000 | 12000 |  | Contact: joshoakhurst@datateer.com
0 | 2026-02-15 | 2026-02-15 | 45 | 60 | 55 | 50 | 33 | 1 | 3000 | 1000 |  | www.datateer.com
-75000 | 2026-01-10 | 2026-01-25 | 60 | 30 | 240 | 220 | 74 | 3 | 22000 | 6500